## Tabelle1
TG-WH 30: Status of WH related activities in the Supplementatry Budget 2020 (version 27 April 2020)
| Sub- Theme |  | Planned activities/deliverables | Status April 2020 | Estimated costs 2020 for funding by the states parties | Proposed share D | [5 empty] | Remarks
Main Theme |  | CWSS Account/PIC (person in charge) |  |  |  |  | Pledged share D | Proposed share DK | Pledged share DK | Proposed share NL | Pledged share NL
WORLD HERITAGE
International Cooperation | UNESCO World Heritage Centre | K135 HM |  | Not yet started. Collaboration continued by supporting WHC activities (renewable project, e-meeting on blue carbon) or preparing activities (such as CVI project) with joint interests. | 5000 | 1666 | 2500 | 1666 | 0 | 1666 | 2500 | Follow up of marine litter workshop 2018 (communication and awareness rising of marine litter in WH sites) and of the 4th Marine site managers' conference (Sept 2019). The development of a 3-year project is envisaged to define work themes, activities, outputs and results.
| MOU Korea | TMAP K01 HM | Hosting Study visit North- and South Korean experts (probably May 2020). General MOU activities: participation of Wadden Sea experts. Deliverable: Cooperation strategy and activities in the framework of MoU and Yellow Sea | Preparation of study visit started in 2019 but have been on hold since February 2020 (due to Covid-19 crisis). Plans for a re-start in 2020 have not been discussed yet. | 12000 | 4000 | 6000 | 4000 | 0 | 4000 | 6000 | A decision on the Korean WH application is expected in July 2020 which may also have effects on the current MoU.Therefore further discussion of concrete activities have been postponed to the second half of 2020 (joint workshop, costs depending on meeting venue and number of participants), ( indicative 7.000). A preparation of study visit of North/-South-Korean experts (about 20) has not yet been finalized, funding and organization of the entire 10-day trip will be done by Korea. CWSS plans to host a 2-day workshop with Korean and Wadden Sea managers and scientists (costs about 5.000 €)
| MOU Mauretania | K127 GL | Development Communication plan 2020-2022 with support of UNESCO. | Ongoing. Coordinated by the Flyway steering group. | 5000 | 1666 | 1666 | 1666 | 1666 | 1666 | 1666 | Communication plan 2018-2020 delayed. Produce a documentary on the importance of the three sites for the conservation of migratory birds in four languages (Arabic, French, English, Portuguese). - Produce joint communication media for general public and agencies. - Integrating the three sites PNBA, Wadden Sea and Bijagós with the international networks of centres of environmental interpretation. - Integrate the three sites Wadden Sea, PNBA and Bijagós into the international networks of flyway initiatives. - Development of raising awareness for PNBA in Nouakchott.
| Wadden Sea Flyway Initiative | K107 GL | Capacity building of WH sites along EAF/training courses/application proposal for IKI project"WSFI capacity building project 2020-2021. Programme not developed yet. Report on WSFI flyway monitoring at selected critical sites in January 2020 and preparation of 2021 Flyway counting." | Ongoing. Coordinated by the Flyway steering group. | 145000 | 60000 | 60000 | 10000 | 10000 | 75000 | 75000 | "The capacity building will be funded by BMU with € 60,000 in 2020 and € 60,000 in 2021. It will contain several sub-projects: - training and courses bird protection, - management of wetlands, - awareness raising and information centres, - support in conferences (PAOC), - preparation WSFI IKI project, The flyway monitoring 2020 (estimated costs 75.000€ ) is fully supported by LNV (PRW) by a direct assignment to the executive organisation Sovon. The Danish contribution (in-kind amounting to 10.000€) also supports this monitoring programme. Further communication of WSFI by microwebsite is envisaged to be covered by core budget.
|  |  | Establish an overall program, including the financial resources needed, to secure the basic flyway monitoring for the longterm, including flyway-partners. | Ongoing. Coordinated by the Flyway steering group. | 50000 | 16666 | 16666 | 16666 | 16666 | 16666 | 16666 | The financing of the flyway monitoring from 2021 onwards, is not safeguarded and will need alternative resources. Fund raising concept and implementation program needed to ensure continuous flyway monitoring and the value of the past monitoring results.
|  | GL | Arctic WSFI workshop | Ongoing. Coordinated by the Flyway steering group. | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | Implementation of Flyway Vision in the framework of WSFI. Integration arctic breeding grounds into WSFI. Workshop of WSFI partners with researchers from Arctic countries. Prioritization future support in monitoring, capacity building, research, communication and cooperation. Postponed from 2019 to 2020. Budget already affirmed by Germany in 2019.
WH Brand Management | Brand Activation and Management | K115 WP3 AD | Brand activation various target audiences and stakeholders: - Brand activation guidebook (transnational concept and local implementation) 39,500) - Brand visualization and communication material and modules (e.g. flyers, videos social media) for various target audiences (40,500) - Online branding toolbox for co-branding (47,000) | Draft guidebook completed and feedback is currently being collected by remote (online/phone) communication because of the Covid-19 crisis. Therefore, preparation of the online toolbox postponed to autumn 2020. | 0 | 0 |  | 0 |  | 0 |  | No additional funding from state parties required as it is covered by PROWAD LINK according project work plan 2018 - 2021.
Outreach and Communication | WH Education Strategy | K72 AB | Contract with IWSS (WWF): Implementation of the WH Education Strategy, adopted at the Leeuwarden Conference | Network Group Education and IWSS network meeting postponed to November 2020 (week 45). Development of education material ongoing. New contract with WWF (2020 - 2022) is delayed becaue unclear whether VAT has to be paid. | 40000 | 10000 | 15000 | 10000 | 10000 | 10000 | 15000 | Continuation of networking and communication activities, connecting regional education networks. Development and/or update of trilateral interpretation material, according WH Interpretation Strategy 2018. Work plan 2020-2022 to be envisaged at WSB 30. Proposal 2 is agreed upon; increase to €40,000.00/year. (In Germany the share is divided between SH: € 5000, NLPV NDS €5000 and NP HH €5000).
| General Communication and Awareness WH | K1 and K115 WP 2 AB | Transnational communication and awareness activities on World Heritage for various target audiences and involvement of stakeholders in D, DK and NL. Annual stakeholder forum meeting. | Proceeding according PROWAD Link work plan. Annual stakeholder forum 2020 was postponed to 2021. Core budget financed activies are website maintanence, redesign of the WSWH leaflet and new WSWH video production. | 0 | 0 |  | 0 |  | 0 |  | No additional funding from states parties required as it is covered by PROWAD LINK (according project work plan 2018 -2021) and by the core budget.
| WH Social Media. | K135 AB | Extension of WH communication on social media channels (Facebook, Twitter, Instagram, Youtube), DNA mapping, sharing and placing contents. Further development of strategy and cooperation with partners (action plan, workshop) | Annual workshop postponed to autumn 2020 (date tbc). Group in exchange on Covid-19-related strategies for social media. | 7500 | 2500 | 3750 | 2500 | 0 | 2500 | 3750 | Stauts 2019: The 2nd social media workshop was held in January 2019 . As the anniversary campaign coming up, the workshop was used to create an accompanying social media plan. It was decided to hold the next workshop in January 2020. Although limited to a maximum of 8-10 people, the workshop is open to all social media experts of the TWSC. Planned 2020: Annual workshop in January 2020 with support from an external expert - external expertise: 7000€; event catering: 500€.
Develop and enhance sustainable tourism (STS) and new Action Plan | WH awareness raising at yearly ITB (Berlin) | K136 AD | Awareness raising platform Word Heritage stand at ITB (showcasing the trilateral cooperation, non- commercial with partners from regional, national or international level as UNESCO). | ITB March 2020 was cancelled on short notice due to the Covid-19 crisis. Advance payments to ITB have been refunded. Only stand construction has been partly invoiced (production costs €6.000) and will be distributed accordingly. | 14000 | 7000 | 7000 | 2500 | 0 | 4500 | 7000 | Total costs based on 2019 budget: € 20,000. Basic costs (floor rental) of € 14,000 to be covered by the Trilateral Cooperation (as in 2019). Increasing buying in of partners. (D share: SH 3,000 €, NLPV NDS 3,000 €, NP HH 1,000 €) Connection with stakeholder platform stand provided by PROWAD LINK WP2 (B2B and B2C) (see separate table).
Support Regional Sustainable Development in connection with Nature Protection | Partnership development/Partnership Hub | K01 HM | Establishment of partnership hub. Engaging further strategic partner and development of joint projects. | Ongoing. Coordinated by OPTeam partnership hub. | 20000 | 6666 | 6666 | 6666 | 6666 | 6666 | 6666 | For the establishment of the Partnership Hub and the follow-up of the MOU's signing at 30 June 2019, a coordinating and stimulating effort is required (preinvestment) of an estimated 20.000. Connection with WP 4 of PROWAD LINK.
| PROWAD LINK Project | K115 HM | Co-funding of CWSS activities in PROWAD LINK covering all six work packages (project management, communication, brand activiation, sustainable entrepreneurs, new products and services) (see separate table) | Proceeding according to PROWAD Link work pan. Regular progress reports (#3 submitted on 24 April 2020). | 11200 | 8500 | 5200 | 3000 | 3000 | 3000 | 3000 | PROWAD LINK activities of CWSS according project work plan 2018 - 2021 (see separate table). The total CWSS project budget is 865,982 € of which 50% is funded by Interreg (ERDF) . The 50% CWSS self finance is covered by the core budget (staff, travel cost), rest from the first PROWAD project, and from CWSS surplus 2017. This leaves a gap of € 25,500 for the remiaining two years.Proposal to cover the gap in 2020:: Estimated D share from Schleswig-Holstein 5,200 (The Hamburg share of 5000 was already pledged by LoI Prowad Link). Estimated share of 3,000 each from DK and NL.
Remark 1: Items in green are externally financed (see column Remarks for explanations; externally financed might also include the Länder).